## Identification
Title | TMF Inspection Readiness RACI
Steering Committee Approval Date | 2016-11-09
Authors
Name | Organization | Title
Dorte Frejwald Christiansen | NNIT | Principal Consultant
Contributing Team Members
Name | Organization | Title
Cassandra Schroeder | Intercept Pharmaceuticals | Sr. Clinical Trials Associate
Denise Sturdy | Duke Clinical Research Institute | Regulatory Intelligence Associate
Devaki Khurjekar | PhlexGlobal | Quality Assurance Manager
Donna Dorozinsky | Just in Time GCP | President
Jody Boyles | BD | Clinical Operations Specialist II
Kathie Clark | Wingspan Technology | VP Product Management
Leah Hiebert | Pharm-Olam International | Senior Manager, Clinical Support
Linda Rudolph | Quality Werx, LLC | Owner/Consultant
Lisa Pabion | Sanofi Pasteur | Quality Systems Project Leader
Martin Thorley | Pfizer | Content Management & Authoring Information Management
Michele Atherton | Purdue Pharma | Manager, Records and Systems
Shah Ashraf | TransPerfect | TMF Quality Specialist Life Sciences Solutions
Stacey Jandciu | Janssen | Associate Director, TMF Compliance
Supriya Shoroff | Medivector Inc | Clinical Document Manager (TMF Operations and System management)
Susan Donahue | FHI 360 | Director, Clinical Regulatory and Compliance

## Version History
Version | Steering Committee Approval Date | Changes
1 | 2016-11-09 | N/A

## RACI Instructions
RACI CHART
How to use it
R = RESPONSIBLE | A = ACCOUNTABLE
“The person doing the job” | “The Buck Stops Here”
The ‘responsible’ is the individual(s) who actually completes the task. This person is responsible for action/implementation. Responsibility can be shared. The degree of responsibility is determined by the individual who is "Accountable.” | The accountable person is the one who is ultimately answerable for the correct and thorough completion of the deliverable or task. This includes “yes” or “no” authority and veto power. Only one "A" can be assigned to an action.
C = CONSULT | I = INFORM
“Keep in the Loop” | “Keep in the Picture”
The consult role is individual(s) (often subject matter experts) to be consulted prior to a final decision. This is a predetermined need for two-way communication. Input from the designated position is required. | This is individual (s) who are kept up-to-date on progress, often only on completion of the task or deliverable and who needs to be informed after a decision or action is taken. They may be required to take action as a result of the outcome. It is a one-way communication.
The tasks/process steps in the RACI are grouped to ease the overview. Note that the order of the tasks may not be chronological.

## Roles
Below are examples of Roles that may be involved in TMF Inspection This is not an exhaustive or definitive list Update with your own Roles and insert into the RACI
Internal Quality Auditor
Internal eTMF Administrator
External (Third Party) Auditor
Study Team Lead
IT Lead
Study Team member
TMF/eTMF Business Process Owner
QA Lead
Roles involved in all aspects of the process
Senior management - identify specific functions
Quality Control (verifying TMF Documents)
TMF Management Group/Center of Excellence
Translator to support inspection (if requested or needed)
…
List all relevant roles involved at your organisation

## Inspection Readiness RACI
Legend: R-Responsible, A- Accountable, C- Consulted, I- Informed (see details in Tab 'RACI Instructions')
# | Task Group | Relevant for Paper TMF? | Relevant for eTMF? | Tasks / Process steps | Key elements | Add company specific role2 | Add company specific role3 | Add company specific role4 | Add company specific role5 | Add company specific role6 | Add company specific role7 | Add company specific role8
1 | Coordinate TMF inspection aspects with Health Authority | x | x | Clarify studies in scope with inspector(s) | All aspects of access to system, paper documents
2 | Coordinate TMF inspection aspects with Health Authority |  | x | Clarify need for eTMF system access with inspector(s) | Check how inspector accounts are set up in the system. If generic accounts are used, make sure to get information on the number of inspectors. If the accounts are set up by name, make sure to obtain inspector names. Ensure IT knows time frame for inspection. Confirm if inspectors want to use their own laptops and determine if this request will be allowed. (This may impact network access.)
3 | Coordinate TMF inspection aspects with Health Authority |  | x | Clarify need for system training with inspector(s) | Confirm length of the training and on-site vs. remote (if offered) with Health Authority. Timing of the training; before the inspection or onsite at the initiation of the inspection
4 | Coordinate TMF inspection aspects with Health Authority | x | x | Inform relevant internal stakeholders about inspection scope | Inspection scope gives information on what will be inspected, e.g. trials, sites, processes.
5 | Coordinate TMF inspection aspects with Health Authority |  | x | Inform IT stakeholders about the need for TMF system access | Make sure IT system management and IT support are informed about the inspection and the inspector access to ensure sufficient IT support during the inspection.
6 | Coordinate TMF inspection aspects with Health Authority |  | x | Inform internal functions about need for TMF system access | Ensure all TMF contributors, e.g. functional areas, know that the inspectors will get direct access to the eTMF.
7 | Coordinate TMF inspection aspects with Health Authority |  | x | Involve relevant internal stakeholders about need for inspector system training | Identify who will be giving the training to the inspectors, e.g. a super user, and make sure to inform about the need for training very early to book the resources.
8 | Coordinate TMF inspection aspects with Health Authority | x | x | Confirm with inspector(s) the TMF environment/inventory, i.e. where will TMF be found | The TMF might consist partially of paper, partially electronic records that may be located in different systems.
9 | Plan the inspection | x | x | Create staffing plan / identify and book relevant staff | Include relevant TMF stakeholders to ensure their availability for the inspection. This might be part of an overall stakeholder list or may contribute to such a list.
10 | Plan the inspection | x | x | Preparing training and other briefing materials for inspectors | This could be guidance notes or quick reference guides with screen shots. It could also comprise brief introduction to the TMF process. Finally it could be a roadmap of the TMF content adapted to the trials in scope.
11 | Plan the inspection | x | x | Investigate inspector's background (specialties and interests) | This might be handled by the Quality department but the outcome is important to know to prepare the TMF.
12 | Plan the inspection | x | x | Review findings from previous inspections | Check for specific findings on the TMF (for the same studies or other studies)
13 | Plan the inspection | x | x | Evaluate all audit findings on studies selected for inspection | Check for specific findings on the TMF
14 | Prepare TMF | x | x | Update and review TMF plan and/or TMF content list and determine how the TMF will be presented to the inspector(s) | Note: the TMF content list is the study TMF list, it include only artifact applicable to that specific study, it can also include excused artifact and rationale. Examples of exclusions to what is presented: contracts or audit reports may provided directly or upon request based on the company's approach.
15 | Plan the inspection | x | x | Write inspection plan/strategy
16 | Plan the inspection | x | x | Evaluate need to perform a mock inspection | Depending on inspection experience in the team, size of the inspection a mock inspection might give useful learnings. It could also be considered to request additional internal audits.
17 | Prepare TMF | x | x | Evaluate TMF readiness | TMF Business to support defined responsibilities supporting ongoing inspection readiness. Metrics could be used to evaluate the TMF readiness if available. Check that all expected final versions are available in the TMF.
18 | Prepare TMF | x | x | Complete pre-inspection checklist or procedure | Recommended TMF completeness checks are listed in the pre-inspection checklist available together with this RACI matrix
19 | Logistics | x | x | Inspection Room planning | Book all rooms needed for the inspection; check that size is suitable for the number of inspectors; confirm network access (wired and/or wireless)
20 | Logistics |  | x | Inspection Room inspection / confirmation | Confirmation of technical/hardware needs (hardwired network, projectors, dedicated printers/scanners, monitors)
21 | Prepare inspector system access |  | x | Initiate or request activation/creation of inspector account(s) | Depending on the lead time for activation of the inspector account, this may have to be initiated at a very early time point. It is important to know how many inspector accounts will be needed and scope of the access (when, for how long, which trials).
22 | Prepare inspector system access |  | x | Activate/create inspector account(s)
23 | Prepare inspector system access |  | x | Ensure that only final, approved documents are viewable by the inspector (Read-only permissions) | Have a plan to address requests for working (non final) versions.
24 | Prepare inspector system access |  | x | Test specific inspector account(s)/role(s) - Inspector view works as set up for this inspection - Only documents expected to be viewed can be viewed - start/stop times (if any) have been set properly | Additional consideration: do you need to plan for providing electronic access to media for a health authority who is not accessing an eTMF directly (e.g. browsing files on electronic media)?
25 | Prepare inspector system access |  | x | Prepare hardware setup (screen(s), keyboard, mouse, printer etc.)
26 | Prepare inspector system access |  | x | Test hardware setup (screen(s), keyboard, mouse, printer etc.)
27 | Prepare for availability of documentation in other systems |  | x | Ensure availability of other system owner/SMEs
28 | Prepare for availability of documentation in other systems |  | x | Ensure availability of validation records in case asked | IT QA should know where to find the validation records for the eTMF or other systems if requested, including compliance position on Health Authority guidance such as Part 11, Annex 11, EMA Reflection Paper/MHRA GCP.
29 | Prepare availability of paper records | x | x | Coordinate with Records Management for paper records availability | Ensure that any hard copies with wet ink signatures or other annotations can be retrieved upon request. If scanning tool is not validated, a more extensive set of paper documents may be subject to retrieval.
30 | Prepare availability of paper records |  |  | Arrange to ship paper records to the inspection site/location | If paper records are not archived at the same location as the inspection site, it might be necessary to plan for a shipment of the records. Ensure that time is allotted for shipment and staging.
31 | Prepare availability of paper records |  | x | Know who to contact in cases where the content is held in a different electronic system (i.e. EDC, CTMS etc.)
32 | Prepare availability of paper records | x | x | Assist the inspector(s) in understanding the TMF process at the Sponsor site
33 | Prepare availability of paper records | x | x | Answer any questions related to the TMF process | Consider if the TMF process owner need to be involved
34 | Prepare availability of paper records | x | x | Assist in obtaining the requested documents for the inspector(s)
35 | Prepare availability of paper records | x |  | Maintain list of all TMF documents requested by/provided to inspector(s) | May be needed for eTMF as well if the eTMF cannot automatically produce this list, but this would be challenging if the inspector requests to be left alone.
36 | Prepare availability of paper records | x | x | Take notes of all TMF-related questions and answers between inspector and personnel | Often a QA/Inspection Management responsibility but TMF team may be asked to take TMF related notes.
37 | Prepare availability of paper records | x | x | Coordinate scheduling of key TMF personnel | Key TMF personnel was booked already when planning of the inspection. This coordination is ad hoc coordination needed during the inspection.
38 | Prepare availability of paper records | x | x | Participate and contribute to daily overall debrief meeting
39 | Prepare availability of paper records | x | x | Conduct daily TMF debrief meeting for all of TMF stakeholders | This is relevant if a specific TMF team/group exists. This debrief would cascade information from the overall inspection debrief to the TMF team/group to ensure more efficient debriefs. If no specific TMF team/group exists, this is part of the overall inspection debrief
40 | Prepare availability of paper records | x |  | Prepare documents for the following day | Inspector might request that a number of documents are ready for their review the following day.
41 | IT and eTMF system support |  | x | Provide training on the eTMF system to the inspector(s)
42 | IT and eTMF system support |  | x | Provide eTMF support as needed during the inspection | Include both IT/System and Process support
43 | IT and eTMF system support |  | x | Answer any questions related to upgrades, security etc. for eTMF | Including questions about system validation
44 | After inspection |  | x | Close/deactivate inspector accounts
45 | After inspection | x | x | Return paper documentation to paper archive | Organise and pack paper documents and ensure they are in an archiving-ready state before sending them back to the paper archive.
46 | After inspection | x | x | Conduct final debrief for TMF stakeholders | This is relevant if a specific TMF team/group exists. This debrief would cascade information from the overall inspection debrief to the TMF team/group to ensure more efficient debriefs. If no specific TMF team/group exists, this is part of the overall inspection debrief
47 | After inspection | x | x | Prepare lessons learned | Any process updates needed
48 | After inspection | x | x | Manage corrective actions
49 | After inspection | x | x | Manage outstanding questions/requests after the inspection | If outstanding questions remain after the inspection, provide documented clarification to inspectors after inspection either in person or by post. If by post this must be agreed with the inspectors. Documents or follow-up elements might be provided after the inspection to clarify comments from the inspectors before they become findings.